## Slide 1
GRIDLAB-D Simulation
(Runs for 4s and pauses)
GLM Model
System State
(Controls and Status)
Reports Completion of Simulation
Message_Creation()
Queries for System State
Sends updated control setpoints (switch status, LTC position, and meter connection status status
Multispeak
GetLatestReadings
Message Encoder
Multispeak
ODEventNotification
Message Encoder
Multispeak
Meter Disconnect
Message Encoder
DNP3 Value Status Message Encoder
DNP3 Voltage Control Message
DNP3 Switch Status Control Message
Packet Writer
Triggers 4s Simulation Continuation
Bob
Phil
Tim
File
Pcap File Writer
Packet Replay (Future)
SIMBA
Simulation Configuration File
A
B
C
D
E
F
Note: GridLab-D may not be capable of reporting simulation completions. A hardcoded time delay may be required.

## Slide 2
Message Creation Code & Logic Overview:
Collects and analyzes state data from GridLab-D to determine what messages need to be created.
Meter energy reads and voltage values are communicated after every 15 minutes
Substation switch status and power readings are communicated every 4 seconds (every simulation iteration).
AMI Event Notifications are sent only when voltage or power at AMI meters is beyond a predetermined threshold. (Successful message creation is determined by a specified probability.)
AMI Meter Disconnect messages are generated at each iteration with a specified probability. Disconnected meters are reconnected at each iteration with a specified probability.
DNP3 Voltage Control Messages are issued with some probability and/or delay when substation voltages are observed outside of specified bounds.
DNP3 switch status control messages are generated based on input configuration file.
INPUT configuration file may specify specific messages to send at specified timestamps (i.e. simulation attacks are speciifed as anomalous messages and/or anomalous control commands with a specific timestamp provided.
The Message creation code will write an output file with all the information required to generate messages. (The exact format is still to be designed. However, it is likely that every row in the output file would correspond to a unique message.). The Message Creation Code & Logic will only interact with GridLab-D in real-time. The code will have no direct interactions with the message and/or packet writing software.
Initially this code can run on a local machine. Running this in AWS may be required to run longer, more sophisticated simulation runs (with larger power system models).

## Slide 3
Message Creation Code & Logic Task List (DRAFT):
Verify GridLab-D model file provided by PNNL. [2 Days]
  Model file consists of 1 substation and 5 feeders. The substation consists of two transformers and 23 switches. The feeders are various taxonomic feeders selected by PNNL and have approximately 1000 to 1500 individual meters each.
  Verify and/or collect reasonable input data for the GridLab-D simulation (i.e. load profiles sufficient to run at least a 1 month simulation)
Verify GridLab-D API [2 Days]
  Confirm ability to:
    Read system state variables (including power, energy, voltage values at meters and substation transformers and binary switch status
    Write system state variables (including substation switch status and meter connection status
    Iterate with successive GridLab-D simulations in a continuous fashion (each simulation run will be 4s in duration).
Write script to automate process of importing simulation configuration data, running GridLab-D, retrieving state information, performing simple calculations on state data (e.g. Is power > XXXX kW), and writing setpoint changes based on calculations [2 Days]
Write script to output message contents to a file. (The file format will be determined with help from the message creation team members. Message contents to be specified by message creation team members.) [2 Days]
Determine high level logic for the generation of messages (3 MultiSpeak message types & 3 DNP3 message types) [1 Day]
  Determine the data from GridLab-D required to evaluate the need for a message
  Determine the data from GridLab-D required to generate a message
  Determine the thresholds and/or message creation probabilities that are needed to generate messages
  Determine what configuration information is needed to run simulations with and without specified attacks
Implement and test the logic for creating messages and writing messages to output file. [0.5 days / message type = 3 Days]
Generate simulated test data and train team members on use of the simulation system [2 Days]
Total Estimated Time Required: 14 Days – 3 Weeks
Desired Start: Monday, September 25 (End: Friday, October 13)

## Slide 4
Simulation
Timestamp
Should a message with meter interval reads be generated? (Has 15 minutes elapsed since last meter read message?)
Yes
No
Probability of successful message generation and transmission.
Substation Switch Status
Substation Transformer Status
(Power and Voltage Readings)
Should substation SCADA message be generated?
(Has 4 seconds elapsed since last meter read message?)
No Action
P
Write meter reading message contents to file.
1- P
No Action
Yes
No
Probability of successful message generation and transmission.
No Action
P
Write SCADA status message contents to file.
1- P
No Action
Meter Connect/Disconnect Message Probabilities
For every meter decide whether a meter connect or disconnect message should be generated
P
1- P
Write meter connect/disconnect message contents to file.
No Action
Update Meter Connection Status in GridLab-D
AMI Meter Status
(Connect, kWh, V)
For every meter decide whether a meter alarm message should be generated (compare values against thresholds)
Meter Alarm
Thresholds
Yes
No
Probability of successful message generation and transmission.
No Action
P_2
1- P_2
No Action
Write meter alarm message contents to file.
Example Message Creation Logic (INCOMPLETE DRAFT):
(No attack logic included)
C
B
A
D
Purple = user input
Blue = data from GridLAB-D

## Slide 5
Substation Transformer Status
(=Voltage Readings)
Should any substation SCADA voltage control messages be generated?
(Compare voltage values against specified thresholds.)
Yes
No
Probability of operator action and message transmission to control voltage
No Action
P
Write SCADA voltage control message contents to file.
1- P
No Action
Switch reconfiguration Probabilities
For every switch decide whether a switch status change message should be generated.
P
1- P
Write switch status change control message contents to file.
No Action
Update Switch Status in GridLab-D
Example Message Creation Logic (INCOMPLETE DRAFT):
(No attack logic included)
F
E
Substation voltage control thresholds and probabilities